## Slide 1
ATLASSIAN GUIDE
PROJECT RISK
MANAGEMENT
Identify · Assess · Monitor · Control
Protect your project from uncertainty

## Slide 2
WHAT IS PROJECT RISK MANAGEMENT?
Project risk management is the process of identifying, analyzing, and responding to potential risks that could impact a project's goals — covering scope, timeline, cost, and quality.
PROACTIVE
Anticipate issues before they arise and plan responses in advance
STRUCTURED
Follow a systematic process across the entire project lifecycle
CONTINUOUS
Monitor and update the risk register throughout project delivery

## Slide 3
TYPES OF PROJECT RISKS
SCOPE RISK
Changes in project requirements, unclear deliverables, or uncontrolled scope creep
SCHEDULE RISK
Delays due to resource constraints, dependencies, or unrealistic deadlines
COST RISK
Budget overruns from poor estimates, unexpected expenses, or resource changes
RESOURCE RISK
Unavailability of key team members, skills gaps, or equipment shortages
TECHNICAL RISK
Integration failures, technology limitations, or performance issues
EXTERNAL RISK
Market shifts, regulatory changes, vendor failures, or natural disasters

## Slide 4
THE RISK MANAGEMENT PROCESS
01
IDENTIFY
Brainstorm, use checklists & expert judgment to list all potential risks
02
ANALYZE
Assess probability and impact. Use qualitative & quantitative methods
03
PRIORITIZE
Rank risks using a risk matrix — focus on high-probability, high-impact first
04
RESPOND
Plan responses: Avoid, Transfer, Mitigate, or Accept each risk
05
MONITOR
Track risks continuously, update the register, and adapt as conditions change

## Slide 5
RISK ASSESSMENT MATRIX
PROBABILITY →
I
M
P
A
C
T
↑
LOW
MEDIUM
HIGH
HIGH
MEDIUM
LOW
MEDIUM
HIGH
CRITICAL
LOW
MEDIUM
HIGH
LOW
LOW
MEDIUM
CRITICAL
HIGH
MEDIUM
LOW

## Slide 6
RISK RESPONSE STRATEGIES
AVOID
⊘
Eliminate the threat by changing the project plan. Adjust scope, timeline, or remove risky activities entirely.
e.g. Drop a risky feature from scope
TRANSFER
⇄
Shift the impact of a risk to a third party through contracts, insurance, or outsourcing.
e.g. Purchase insurance or hire contractors
MITIGATE
↓
Reduce the probability or impact of a risk through early action. The most common strategy used in projects.
e.g. Add buffer time to critical deadlines
ACCEPT
✓
Acknowledge the risk and prepare a contingency plan. Best for low-priority risks with limited response options.
e.g. Create a contingency budget reserve

## Slide 7
THE RISK REGISTER
A risk register is a living document that tracks all identified risks throughout the project. It is the foundation of effective risk management.
Risk ID
Unique identifier for tracking
Description
Clear explanation of the risk
Probability
Likelihood of occurrence (H/M/L)
Impact
Severity if the risk occurs (H/M/L)
Owner
Responsible team member
Response
Planned action (Avoid/Transfer/Mitigate/Accept)
Status
Open / In Progress / Closed
RISK
PROB
IMPACT
RESPONSE
Scope creep
H
H
Avoid
Key dev leaves
M
H
Mitigate
Budget overrun
M
M
Transfer
API dependency
L
H
Mitigate
Market change
L
M
Accept

## Slide 8
BEST PRACTICES
1
Involve Your Whole Team
Everyone on the team has unique perspective on what could go wrong. Include stakeholders in risk workshops from day one.
2
Update the Register Regularly
Risks evolve as the project progresses. Schedule recurring reviews to add new risks and close resolved ones.
3
Use a Risk Matrix
Visualize risk levels using a probability vs. impact grid to quickly identify which risks demand immediate attention.
4
Assign Clear Ownership
Every risk must have a named owner. Accountability ensures risks are actively monitored and not left unaddressed.
5
Plan for the Unknown
Reserve time and budget contingencies for risks you cannot predict. A 10–15% buffer is a widely recommended minimum.
6
Learn from Past Projects
Conduct post-mortems and maintain a lessons-learned database to inform risk planning on future projects.

## Slide 9
KEY TAKEAWAYS
1
Risk management is not optional — it is essential to project success
2
Identify risks early, before they become costly issues
3
Not all risks are equal — prioritize using probability × impact
4
Every risk needs an owner and a documented response plan
5
The risk register is a living document — update it continuously
6
Good risk management reduces surprises and builds stakeholder confidence

## Slide 10
START MANAGING
RISKS TODAY
Protect your project · Empower your team · Deliver with confidence
atlassian.com/work-management/project-management/project-risk-management